SMAART INSTITUTE

Mobile Application (React Native)

Software Requirements Specification & Development Roadmap

Companion mobile app to the SMAART Institute Web Dashboard

| Field | Value |
| --- | --- |
| Document Version | 1.0 (Draft for Planning) |
| Date | 29 July 2026 |
| Prepared For | SMAART Institute — Product & Engineering |
| Target Platforms | iOS 14+ and Android 9+ (API 28+) |
| Reference System | SMAART Institute Web Dashboard (existing React + Node/Express + MongoDB app) |
| Primary Framework | React Native |

# 1. Document Control

## 1.1 Revision History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 1.0 | 2026-07-29 | Planning Draft | Initial requirements & roadmap, derived from the existing web dashboard's feature set |

## 1.2 How to Use This Document

This document is written to take you from "I need to build a React Native app" to a concrete, phased execution plan. Read Sections 1–4 for context and scope, Section 5 for exactly what to build (feature-by-feature, in the same structure as the existing web dashboard), Sections 6–9 for how to build it technically, and Sections 11–14 for the week-by-week plan, testing, and release process. Section 15 lists risks worth deciding on early, and the Appendix gives a full screen inventory you can turn directly into a Jira/Trello backlog.

# 2. Introduction

## 2.1 Purpose

This document defines the functional requirements, non-functional requirements, technical approach, and phased development roadmap for a React Native mobile application for SMAART Institute. The goal is feature parity, on iOS and Android, with the existing SMAART Institute Web Dashboard (the "Reference System"), while adapting browser-only mechanisms — particularly the browser-based proctoring engine — to native mobile equivalents.

## 2.2 Scope

In scope for the mobile app (Phase 1, student-facing):

- Authentication & onboarding (institution selection, signup/OTP, login, password reset, secure sessions)

- Staged assessment engine: Baseline (T1) → Capacity (T2) → Capability (T3) → Leadership (T4), plus the AIQ assessment, skill assessments and micro-assessments

- Proctored testing, adapted to native camera/mic/app-lifecycle APIs

- Learning & course platform: catalogue, enrollment, video player, module tasks, notes, CGPA calculator, certificates

- Career & placement tools: AI Career Coach, resume builder, career roadmap/insights, job board, skills passport

- Wellbeing, community & gamification: vision board, MindCare, community feed/groups, badges, streaks

- Support & notifications: tickets, grievances, native push notifications

Out of scope for Phase 1 (remain on the web dashboard):

- Admin/moderator back-office consoles (course & question authoring, proctoring review console, moderation queue, analytics dashboards)

- College-admin content management (announcements/banner authoring)

- Any workflow that is exclusively used by staff rather than students, unless explicitly added to a later phase (see Section 11, Phase 10)

The existing Node/Express + MongoDB backend and REST API are reused as-is wherever possible. New or adapted endpoints are called out explicitly where the mobile client's needs diverge from the web client (e.g. proctoring heartbeats under iOS app backgrounding, push-token registration).

## 2.3 Reference System Summary

The current web dashboard is a full institute LMS + assessment + career platform, organized into these modules — this mobile app should mirror the same modules and the same underlying data/API, just delivered through native screens:

| Module | What it does today (web) |
| --- | --- |
| Authentication | Institution-scoped login, signup with OTP verification, forced first-login password change, forgot/reset password, JWT sessions |
| Assessments | Multi-stage assessment engine (T1–T4 + AIQ), Likert/Likert-7/MCQ question types, stage-gated progression, results & quotient analysis |
| Proctoring | Face registration & continuous match, attention/liveness checks, tab-switch/fullscreen/second-screen detection, audio monitoring, server-side risk scoring, held/review workflow |
| Learning | Course catalogue, enrollment, video player, day-by-day module tasks, notes, CGPA calculator, verifiable certificates |
| Career & Placement | AI Career Coach chat, resume builder, career roadmap/market insights, job/placement board, skills passport & badges |
| Community & Wellbeing | Vision board, MindCare sessions, community posts/groups, streaks, achievements |
| Support | Support tickets, grievances, notification center |

## 2.4 Definitions & Abbreviations

| Term | Meaning |
| --- | --- |
| RN | React Native |
| SRS | Software Requirements Specification |
| FR / NFR | Functional Requirement / Non-Functional Requirement |
| OTP | One-Time Password |
| MCQ | Multiple-Choice Question |
| AIQ | AI/digital-literacy assessment used alongside T1–T4 |
| JWT | JSON Web Token, used for session authentication |
| FCM / APNs | Firebase Cloud Messaging / Apple Push Notification service |
| MoSCoW | Prioritization scale: Must have, Should have, Could have |
| EAS | Expo Application Services (build/submit/update pipeline) |

# 3. Product Overview

## 3.1 Product Perspective

The mobile app is a companion/replacement client for students, talking to the same institution-scoped backend as the web dashboard. It is not a rebuild of the backend — it is a new presentation layer, plus the native adaptations needed for camera/microphone-based proctoring and app-lifecycle events that don't exist in a browser.

## 3.2 Target Users

| Role | Mobile App (Phase 1) | Notes |
| --- | --- | --- |
| Student | Full access — this is the primary persona | All modules in Section 5 |
| Teacher / Coach | Not included in Phase 1 | Candidate for Phase 2 (mentor console, light read/write) |
| College Admin | Not included in Phase 1 | Candidate for Phase 2 (push announcements, read-only stats) |
| Admin / Moderator | Not included — continue using the web dashboard | Out of scope; back-office tools stay web-only |

## 3.3 Assumptions & Constraints

- The existing REST API and MongoDB data model are reused; institution (college) scoping works the same way as on web.

- Students may sit proctored exams on a range of Android devices with varying camera/CPU quality — proctoring checks must degrade gracefully rather than block low-end devices outright.

- Camera and microphone permissions are mandatory for proctored assessments and must be explained to the user before being requested (App Store/Play Store review requirement).

- iOS cannot be forced into a true fullscreen/kiosk mode by a third-party app — this is a platform limitation, not a bug, and is addressed via a policy-level mitigation in Section 7.

- Network connectivity will be inconsistent for some students; the assessment engine needs local answer buffering and resumable sessions rather than assuming an always-on connection.

# 4. User Roles & Permissions

The backend already defines roles: admin, moderator, consultant, college_admin, coach, student, teacher. The mobile app in Phase 1 only authenticates the student role; the app should still check the role claim in the JWT and show a friendly "please use the web dashboard" message if a non-student account logs in, rather than silently failing.

| Role | Description | Mobile Access |
| --- | --- | --- |
| Student | Enrolled learner taking assessments and courses | Full access to all Phase 1 modules |
| Teacher | Manages content/students on web | Blocked in Phase 1 with redirect-to-web message |
| Coach | Mentors students, reviews progress on web | Blocked in Phase 1 with redirect-to-web message |
| College Admin | Manages institution-level content on web | Blocked in Phase 1 with redirect-to-web message |
| Consultant / Moderator / Admin | Back-office / platform staff | Not applicable to the mobile app |

# 5. Functional Requirements

Requirements are grouped by module, in the same structure as the reference web app, and prioritized using MoSCoW (Must / Should / Could) for Phase 1 planning.

## 5.1 Authentication & Onboarding

| ID | Requirement | Description | Priority |
| --- | --- | --- | --- |
| FR-AUTH-01 | Institution selection | First-run screen where the student selects their college/institute before any login, matching the web app's institution-scoped context. | Must |
| FR-AUTH-02 | Signup with OTP | Multi-step signup: initial details → email OTP verification (send/verify/resend) → comprehensive profile form → success screen. | Must |
| FR-AUTH-03 | Login with password | Standard email/username + password login against the selected institution. | Must |
| FR-AUTH-04 | Login OTP verification | Optional/step-up OTP verification on login (verify/resend), mirroring the web flow. | Should |
| FR-AUTH-05 | Forced password change | First-login and admin-forced password resets must be enforced before the app allows access to other modules. | Must |
| FR-AUTH-06 | Forgot / reset password | Email-OTP-based password reset flow. | Must |
| FR-AUTH-07 | Secure session storage | JWT stored in platform secure storage (Keychain on iOS / Keystore-backed storage on Android), never in plain AsyncStorage. | Must |
| FR-AUTH-08 | Silent token renewal | Automatic refresh of the session token before expiry, with a session-expiry warning if renewal fails. | Must |
| FR-AUTH-09 | Biometric login | Face ID / Touch ID / fingerprint unlock as a native-only convenience layered on top of the stored session. | Should |
| FR-AUTH-10 | Single active session | Native equivalent of the web "single tab guard": logging in on a new device should warn about, or invalidate, the previous session. | Should |
| FR-AUTH-11 | Device fingerprinting | Send a device identifier with auth requests so the existing device-fingerprint middleware and rate limiting continue to work. | Must |
| FR-AUTH-12 | Onboarding profile completion | Post-signup "add details" / onboarding steps before reaching the dashboard. | Should |

## 5.2 Assessments & Testing Engine

| ID | Requirement | Description | Priority |
| --- | --- | --- | --- |
| FR-ASMT-01 | Assessments dashboard | Stage cards for T1 (Baseline), T2 (Capacity), T3 (Capability), T4 (Leadership) and AIQ, each showing lock/unlock status, question count and duration. | Must |
| FR-ASMT-02 | Question renderer | Supports Likert, Likert-negative, Likert-7 and MCQ question types with the same scoring/quotient tagging as the backend. | Must |
| FR-ASMT-03 | Timed session with resume | A running assessment must survive the app being killed or backgrounded — timer state is server-authoritative and the session resumes correctly on relaunch. | Must |
| FR-ASMT-04 | Offline answer buffering | Answers are cached locally and synced automatically once connectivity returns, so a brief network drop doesn't lose progress. | Must |
| FR-ASMT-05 | Stage-gating logic | Reproduces the existing S10/S19/S25 course-stage gating so a student can't jump ahead of what the backend allows. | Must |
| FR-ASMT-06 | Skill assessment player | Per-skill assessment flow reachable from a skill's detail screen. | Must |
| FR-ASMT-07 | Micro-assessments / quizzes | Shorter module-level quizzes, separate from the staged assessments. | Should |
| FR-ASMT-08 | Results & quotient analysis | Post-assessment analysis, motivational messaging and quotient-grid visualizations, matching the web reports. | Must |
| FR-ASMT-09 | Submission & review states | Clear UI for "submitted", "pending review" and "results available" states. | Should |

## 5.3 Proctoring System (Mobile Adaptation)

This is the highest-risk module to port, because several web mechanisms (fullscreen enforcement, tab-switch detection, second-screen detection) have no exact native equivalent. Section 7 maps each web mechanism to its closest native counterpart — read it alongside this table.

| ID | Requirement | Description | Priority |
| --- | --- | --- | --- |
| FR-PROC-01 | Camera/mic permission flow | Clear, policy-compliant pre-permission explanation screen before requesting camera and microphone access. | Must |
| FR-PROC-02 | Face registration | Pre-exam capture of a reference face embedding (multi-frame average), stored the same way as the web flow (via the existing backend/Cloudinary pipeline). | Must |
| FR-PROC-03 | Continuous face-match verification | Periodic on-device face-match checks during the exam, sending only compact results (not raw video) to the server to save bandwidth and battery. | Must |
| FR-PROC-04 | Presence & attention detection | Detect face absent, face covered, multiple faces, and use head-pose/eye signals as an attention proxy. | Must |
| FR-PROC-05 | Randomized liveness checks | Periodic on-screen prompts (e.g. "look at the camera") the student must respond to, mirroring the web attention-check modal. | Should |
| FR-PROC-06 | App background/foreground detection | Native equivalent of tab-switch/window-blur detection using the OS app-state API; logged as a proctoring event. | Must |
| FR-PROC-07 | Kiosk-style focus mode | Where the OS allows it (Android Screen Pinning), prompt the student to enable single-app mode; on iOS, show an instructional Guided Access prompt since it can't be forced programmatically. | Should |
| FR-PROC-08 | Screenshot / screen-recording flagging | Block screenshots on Android (secure flag) and detect/log screen-recording attempts on iOS (best-effort, since iOS can't block it outright). | Should |
| FR-PROC-09 | Audio monitoring | Sustained-voice and prolonged-silence detection from the microphone stream, matching the web thresholds. | Should |
| FR-PROC-10 | Heartbeat / liveness ping | Periodic ping while the app is foregrounded so the server can detect a session "going dark"; explicit paused state if backgrounded past the grace period. | Must |
| FR-PROC-11 | Inactivity detection | Idle-timer based presence check after a period with no touch interaction. | Should |
| FR-PROC-12 | Server-authoritative decisioning | All risk scoring and tier decisions (ok → warn → pause → held) stay server-side, reusing the existing policy engine with new mobile event types. | Must |
| FR-PROC-13 | Evidence capture & upload | Snapshot evidence captured and uploaded securely, with the same ownership-verified access control as the web app. | Must |
| FR-PROC-14 | Proctoring status UI | Overlay, warning modal, pause screen and "assessment held" screen, mirroring the web components 1:1. | Must |
| FR-PROC-15 | Flag-only mode support | Client must support the server's FLAG_ONLY_MODE (non-interrupting monitoring, judged at submission) as well as interrupting mode. | Must |

## 5.4 Learning & Course Platform

| ID | Requirement | Description | Priority |
| --- | --- | --- | --- |
| FR-LRN-01 | Course catalogue & enrollment | Browse available courses and enroll, matching backend enrollment rules. | Must |
| FR-LRN-02 | Video course player | Native video playback with progress tracking; background/picture-in-picture playback as a stretch goal. | Must |
| FR-LRN-03 | Module tasks | Day-by-day module tasks: flashcards, MCQ practice, reflections and submissions. | Must |
| FR-LRN-04 | Progress tracking | Syncs enrollment/progress state with the backend (UserProgress, Enrollment models). | Must |
| FR-LRN-05 | Notes | Personal note-taking tied to courses/modules. | Should |
| FR-LRN-06 | CGPA calculator | Same calculation logic as the web tool. | Could |
| FR-LRN-07 | Certificates | View, download and share verifiable certificates (deep link to the existing verification page). | Must |

## 5.5 Career & Placement

| ID | Requirement | Description | Priority |
| --- | --- | --- | --- |
| FR-CAR-01 | AI Career Coach chat | Conversational career-guidance chat interface. | Must |
| FR-CAR-02 | Resume builder | Mobile-adapted resume forms and templates, with PDF export/share. | Should |
| FR-CAR-03 | Career roadmap & insights | Roadmap, market-intelligence and skills/certification panels. | Should |
| FR-CAR-04 | Interview prep content | Interview-preparation library/content screens. | Could |
| FR-CAR-05 | Job / placement board | Browse listings (company, role, deadline, skills, job type), view details, apply and track application status. | Must |
| FR-CAR-06 | Skills passport & badges | Verifiable skill credentials and badges, with deep links to the public verification pages. | Should |

## 5.6 Wellbeing, Community & Gamification

| ID | Requirement | Description | Priority |
| --- | --- | --- | --- |
| FR-COM-01 | Vision board | Create and browse a personal vision board (gallery + editor). | Could |
| FR-COM-02 | MindCare sessions | Wellbeing/motivational content sessions. | Could |
| FR-COM-03 | Community feed | Posts, groups/group chat and reactions, with the same moderation rules enforced server-side. | Should |
| FR-COM-04 | Streaks & achievements | Gamified streaks, badges and achievements, ideally paired with push-notification nudges. | Should |
| FR-COM-05 | To-do tracker | Personal task tracker; native reminders as an enhancement. | Could |

## 5.7 Support & Notifications

| ID | Requirement | Description | Priority |
| --- | --- | --- | --- |
| FR-SUP-01 | Support tickets | Create, view and track support tickets. | Must |
| FR-SUP-02 | Grievances | Submit and track grievances. | Should |
| FR-SUP-03 | Push notifications | Native push (FCM/APNs) replacing the web bell/toast — categories: results ready, proctoring status, announcements, community activity. | Must |
| FR-SUP-04 | In-app notification center | Persistent, filterable list of past notifications. | Must |

## 5.8 Explicitly Out of Scope (Phase 1)

Admin course/question authoring, the proctoring review console, the moderation queue and analytics dashboards remain web-only. If a staff member needs occasional mobile access, the recommended interim solution is an in-app web view deep link into the existing web dashboard rather than rebuilding those consoles natively — see Section 11, Phase 10 for when to revisit this.

# 6. Non-Functional Requirements

| Category | Requirement |
| --- | --- |
| Performance | Core screens render in under 2 seconds on a mid-tier device; on-device face detection runs at ≥5 fps without dropping UI frames. |
| Security | JWTs stored in Keychain/Keystore-backed secure storage; certificate pinning on API calls; no plaintext credential storage; proctoring media encrypted in transit. |
| Offline resilience | Cached read-only views for course content and notifications when offline; assessment answers buffered locally and synced on reconnect. |
| Compatibility | iOS 14+ and Android 9+ (API 28+); tested across a representative range of camera hardware. |
| Accessibility | Font scaling and screen-reader labels on all critical flows (auth, assessment, results). |
| Localization | Architecture ready for multiple languages; English for Phase 1. |
| Scalability | Backend must handle concurrent web + mobile proctoring sessions per institution without a dedicated mobile-only backend. |
| Privacy & compliance | Explicit camera/mic consent screens, a defined retention policy for proctoring evidence, and alignment with applicable data-protection requirements. |
| Battery / resource use | On-device inference tuned to limit battery drain across a typical exam-length session (60–90 minutes). |
| App-store compliance | Proctoring behavior must comply with Apple App Store Review Guidelines and Google Play policy on background camera/mic use — see Section 15. |

# 7. Web → Native Mechanism Mapping

The existing proctoring engine relies on several browser-only APIs. This table is the key reference for the engineering team building Phase 3 (Section 11) — it is the single biggest source of scope surprises if skipped.

| Web Mechanism | Native Equivalent | Notes |
| --- | --- | --- |
| Tab-switch (visibilitychange) | AppState 'background' / 'active' events | Direct equivalent, well supported on both platforms. |
| Window blur / minimize | AppState + focus listeners | Same event source as above on mobile. |
| Fullscreen enforcement + 15s grace | No forced-fullscreen API exists on mobile | Cannot be programmatically forced, especially on iOS. Mitigate with an on-screen instruction, an optional OS-level single-app mode (Android Screen Pinning / iOS Guided Access), and rely on server-side risk scoring as the real backstop. |
| Second-screen detection | Not directly available on mobile | Substitute with screen-mirroring detection (Android UiModeManager / iOS AirPlay/external-display notifications) where feasible; treat as best-effort, not guaranteed. |
| Virtual-camera detection | Native camera device enumeration | Check the platform's camera device list for non-physical camera identifiers. |
| face-api.js / ONNX in the browser | react-native-vision-camera + on-device ML Kit / TensorFlow Lite face detection | Runs on-device to avoid streaming raw video to the server. |
| getUserMedia media stream | react-native-vision-camera (video) + native audio module (mic level) | Native camera/mic APIs, permission-gated. |
| Cloudinary snapshot upload | Same backend endpoint, multipart upload from the RN client | No backend change needed here. |
| Duplicate exam window check | Single-device/session-token enforcement via device ID | Server already tracks session ownership; extend the check to device ID instead of window/tab ID. |

# 8. Technology Stack Recommendation

| Concern | Recommendation | Why |
| --- | --- | --- |
| Framework | React Native via Expo, using a custom development client (Expo Prebuild), not the fully managed workflow | Custom native modules are required from day one for proctoring (vision-camera, on-device ML), so a pure managed workflow won't be enough — but Expo tooling still speeds up everything else (builds, OTA updates, config). |
| Navigation | React Navigation — bottom tabs for the main sections, stack navigators within each | Matches the module-based IA in Section 10 and is the de-facto standard. |
| Server state | TanStack Query (React Query) | Handles caching, retries and background refetch against the existing REST API with minimal boilerplate. |
| Client/app state | Zustand (or Redux Toolkit if the team already knows Redux) | Lightweight state for auth session, active exam session, proctoring status. |
| Forms & validation | React Hook Form + Zod | Matches common patterns for the signup/profile/resume-builder forms. |
| Camera & vision | react-native-vision-camera + ML Kit Face Detection (or a TensorFlow Lite model matching the web's embedding format) | Best-supported native camera library with frame-processor hooks for real-time face analysis. |
| Audio monitoring | expo-av / react-native-audio-recorder | Mic-level sampling for the voice/silence checks in FR-PROC-09. |
| Secure storage | expo-secure-store or react-native-keychain | Required for FR-AUTH-07 (secure JWT storage). |
| Push notifications | expo-notifications backed by Firebase Cloud Messaging (Android) and APNs (iOS) | Standard cross-platform push setup. |
| Networking | Axios (REST) + socket.io-client if the backend already uses WebSockets for chat/real-time | Reuses the existing API contract directly. |
| Crash & analytics | Sentry (or Firebase Crashlytics) | Needed from the first beta build, especially for proctoring-related crash triage. |
| CI/CD | EAS Build + EAS Submit, EAS Update for JS-only OTA patches | Avoids full store resubmission for non-native fixes. |
| Testing | Jest + React Native Testing Library for units/components, Detox for end-to-end | Covers the critical login → assessment → submit flow end-to-end. |

# 9. High-Level Architecture

The mobile app is a new client, not a new backend. It talks to the same Node/Express REST API and MongoDB-backed data model that the web dashboard already uses:

- RN app (iOS/Android) ↔ existing Express REST API (reuse as-is; add a small number of mobile-specific endpoints, e.g. push-token registration and mobile proctoring event ingestion under a versioned path such as /api/mobile/v1).

- Same JWT-based auth model, same institution scoping, same MongoDB models (User, Assessment, Result, ProctoringSession/Event, Course, Enrollment, Certificate, Badge, Notification, SupportTicket, JobApplication, etc.).

- Cloudinary continues to store proctoring snapshot evidence and profile/resume media.

- The existing server-side proctoring policy engine (config/proctoringPolicy.js, proctoringController.js) is reused unchanged for risk scoring — the mobile client only needs to send new event types where the detection mechanism differs (Section 7).

- Firebase Cloud Messaging / APNs added for push notifications, replacing the web bell/toast system.

# 10. Information Architecture & Navigation

Bottom-tab navigation for the student role, mirroring the module structure of the web dashboard:

| Tab | Contains |
| --- | --- |
| Home | Dashboard summary, announcements, streaks/badges, quick links |
| Assessments | Assessments dashboard, stage/skill/micro-assessment players, results & analysis |
| Learning | Course catalogue, enrolled courses, course player, module tasks, notes, certificates, CGPA calculator |
| Career | AI Career Coach, resume builder, roadmap/insights, job board, skills passport |
| Community | Community feed, groups, vision board, MindCare |
| Profile / More | Profile & settings, notifications center, support tickets, grievances, logout |

Full-screen (non-tab) flows: institution selection, signup/OTP, login/OTP, forgot/reset password, the assessment player itself (opens full-screen to minimize distraction and support the proctoring overlay), and all proctoring status screens (setup, overlay, warning, pause, held).

# 11. Step-by-Step Development Roadmap

Phased for a small focused team (2–4 engineers + 1 designer + 1 QA). Durations assume that discovery happens before Phase 1 starts and that the backend team is available for the mobile-specific endpoint additions called out in Section 9. Adjust durations proportionally for a larger or smaller team.

| Phase | Duration | Key Deliverables |
| --- | --- | --- |
| Phase 0 — Discovery & Setup | 1–2 wks | Finalize scope against this document; backend API audit & gap list; UI kit/design system; RN project scaffold (Expo + dev client); CI pipeline; dev/staging/prod environment configs; auth technical spike. |
| Phase 1 — Core Auth & Navigation | 2 wks | Institution selector; signup + OTP; login + OTP; forced password change; forgot/reset password; secure token storage; biometric login; tab/stack navigation shell (Section 10). |
| Phase 2 — Assessment Engine | 3–4 wks | Assessments dashboard; question renderer (Likert/Likert-7/MCQ); timed session with resume; offline answer buffering; stage-gating logic; results/analysis screens. |
| Phase 3 — Proctoring Adaptation | 4–5 wks (highest risk) | Camera/mic permission UX; face registration; on-device face-match model integration; attention/liveness checks; AppState-based background detection; heartbeat; evidence upload; full status UI (overlay/warning/pause/held); new mobile event types wired into the existing server policy engine; early App Store/Play Store policy review. |
| Phase 4 — Learning & Course Platform | 2–3 wks | Catalogue & enrollment; video player; module tasks; notes; CGPA calculator; certificates. |
| Phase 5 — Career & Placement | 2–3 wks | AI Career Coach chat; resume builder; roadmap/insights panels; job board & applications; skills passport. |
| Phase 6 — Community, Wellbeing & Gamification | 2 wks | Vision board; MindCare; community feed/groups; badges/streaks; notification center UI. |
| Phase 7 — Support & Notifications | 1 wk | Support tickets; grievances; push-notification wiring (FCM/APNs) across all modules. |
| Phase 8 — QA, Hardening & Beta | 2–3 wks | Full regression pass; device-matrix testing; proctoring accuracy testing across lighting/devices (Section 13); security review; performance profiling; closed beta via TestFlight / Play Internal Testing. |
| Phase 9 — Store Submission & Launch | 1–2 wks | Store listing assets; privacy nutrition labels; App Store/Play review submission with proctoring/camera usage clearly disclosed; phased rollout; monitoring/alerting live. |
| Phase 10 — Post-Launch Iteration | Ongoing | Crash/analytics monitoring; feedback loop; evaluate Teacher/Coach and College Admin mobile access as a Phase 2 initiative. |

Estimated total: roughly 20–26 weeks (about 5–6 months) end-to-end for Phases 0–9 with a small focused team, running most phases back-to-back with some overlap (e.g. Phase 4 design can start while Phase 3 engineering is still underway).

# 12. Milestone Summary

| Milestone | Target (cumulative) | Exit Criteria |
| --- | --- | --- |
| M1 — Project foundation ready | End of week 2 | RN app builds on both platforms; CI green; auth spike validated against the real API. |
| M2 — Students can log in and navigate | End of week 4 | Phase 1 complete; full auth flow and navigation shell demoable. |
| M3 — A student can take a non-proctored assessment end-to-end | End of week 8 | Phase 2 complete; results screen shows real quotient data. |
| M4 — A student can take a fully proctored assessment | End of week 13 | Phase 3 complete; proctoring events visible in the existing admin review tools. |
| M5 — Feature-complete build | End of week 20 | Phases 4–7 complete; every module in Section 5 is present. |
| M6 — Beta sign-off | End of week 23 | Phase 8 complete; no P1 bugs open; pilot institution UAT passed. |
| M7 — Public launch | End of week 25 | Phase 9 complete; live on both app stores. |

# 13. Testing Strategy

- Unit testing (Jest) for utilities, hooks and state logic.

- Component testing (React Native Testing Library) for screens and shared UI.

- Integration testing for the API layer against a staging backend.

- End-to-end testing (Detox) for the critical path: login → start assessment → answer → submit → view result.

- Manual device-lab testing across a representative spread of iOS/Android versions and camera qualities.

- Proctoring-specific test plan: low light, no camera available, multiple faces in frame, face covered, app backgrounded mid-exam, screenshot/screen-recording attempt, network drop mid-exam, low-end-device frame-rate check.

- Security testing: token storage, API auth boundaries, certificate pinning.

- User acceptance testing (UAT) with one pilot institution before full rollout.

# 14. Deployment & Release Plan

- Three environments — dev, staging, prod — each with its own API base URL and Firebase project.

- EAS Build profiles per environment; TestFlight for iOS beta, Play Internal Testing track for Android beta.

- Phased/staged rollout percentage on both stores for the initial public release.

- EAS Update (or CodePush) for JS-only OTA fixes; any native-module change still requires a full store resubmission.

- Defined rollback plan: ability to halt a staged rollout and/or ship an OTA revert within the same day.

# 15. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| iOS cannot force fullscreen/kiosk mode | Rely on server-side risk scoring plus explicit on-screen warnings and clear institution policy communication rather than a hard technical block (see Section 7). |
| App Store rejection for continuous camera/mic monitoring | Clear consent screens, an explicit privacy policy, minimizing background capture, and following platform guidelines closely; default to FLAG_ONLY_MODE as the safer posture where policy allows. |
| On-device ML performance varies across low-end Android devices | Device tiering, a lower-frequency check fallback, and a cloud-assisted verification fallback for devices that can't sustain on-device inference. |
| Connectivity loss during a timed exam | Local answer buffering plus server-side session resume and the existing grace-period policy (already present in the backend). |
| Battery drain from continuous camera/mic use | Optimize sampling rate, warn users to charge before starting an exam, and cap continuous-checks duration to the exam length. |
| Scope creep replicating the full admin console on mobile | Explicit out-of-scope declaration (Section 2.2 and 5.8); revisit only as a distinct Phase 2 initiative. |

# Appendix A — Screen Inventory

A near-complete list of screens, organized by module — ready to convert directly into backlog tickets.

| Module | Screen | Purpose |
| --- | --- | --- |
| Auth | Institution Selector | Choose college/institute before login |
| Auth | Signup (Initial) | Start signup, collect basic info |
| Auth | OTP Verification | Verify email via OTP (signup & login) |
| Auth | Comprehensive Signup | Full registration form |
| Auth | Signup Success | Confirmation screen |
| Auth | Login | Password login |
| Auth | Forced Password Change | First-login mandatory password reset |
| Auth | Forgot / Reset Password | OTP-based password recovery |
| Auth | Onboarding / Add Details | Post-signup profile completion |
| Home | Dashboard | Summary, announcements, quick links |
| Assessments | Assessments Dashboard | Stage cards, lock/unlock status |
| Assessments | Assessment Player | Question renderer, timer, navigation |
| Assessments | Skill Assessment Player | Per-skill assessment |
| Assessments | Micro-Assessment List / Player | Short module-level quizzes |
| Assessments | Analysis / Results | Post-assessment quotient results |
| Assessments | Motivational / Quotients Grid | Results visualization |
| Proctoring | Proctoring Setup | Face registration, camera/mic checks |
| Proctoring | Proctoring Overlay | In-exam status indicator |
| Proctoring | Warning Modal | Violation warning |
| Proctoring | Attention Check | Randomized liveness prompt |
| Proctoring | Pause / Inactivity Overlay | Session paused state |
| Proctoring | Assessment Held | Session held for review |
| Learning | Course Catalogue | Browse & enroll |
| Learning | Course Player | Video playback |
| Learning | Module View / Tasks | Day-by-day tasks, flashcards, MCQ practice |
| Learning | My Notes | Personal notes |
| Learning | CGPA Calculator | Grade calculation tool |
| Learning | Certificates | View/download/share, verification link |
| Career | AI Career Coach Chat | Conversational guidance |
| Career | Resume Builder | Templates & editor |
| Career | Career Roadmap / Insights | Market intelligence, skills panels |
| Career | Interview Prep | Prep content library |
| Career | Placement Board / Detail | Job listings & application tracking |
| Career | Skills Passport | Verifiable credentials |
| Community | Vision Board Gallery / Editor | Personal vision board |
| Community | MindCare Sessions | Wellbeing content |
| Community | Community Feed / Groups | Posts, group chat, reactions |
| Community | Badges / Streaks | Gamification |
| Support | Support Tickets | Create/view/track tickets |
| Support | Grievances | Submit/track grievances |
| Support | Notification Center | All past notifications |
| Profile | Profile & Settings | Account details, preferences, logout |

# Appendix B — Backend & API Reuse Notes

- The large majority of the existing ~50 backend route modules (auth, users, students, courses/enrollments, assessments, results, question banks, certificates, badges, resumes, career agent, community, notifications, tickets, grievances, job applications, etc.) can be called by the mobile client as-is.

- New or adapted endpoints to plan for: mobile proctoring event ingestion (new event types from Section 7), push-token registration (for FCM/APNs), and an app-version / force-update check endpoint.

- No changes are expected to the server-side proctoring policy engine's decision logic — only the set of event types it can receive grows.